## Sheet1
Iter | Component | Task | Units | Vel | Est Hr | Compl | Real Hr | Real Vel | CplUnits
1 | pe/EclipsePE | plug-in development, verbatim text entry only | 7 | 0.65 | 10.7692 | 50% | 4 | 0.875 | 3.5
1 | pe/EclipsePE | process text into code (RPC -> Ruby), source type detection | 5 | 0.7 | 7.1429 | 20% | 2 | 0.5 | 1
1 | pe/core | C++/Java support | 8 | 0.78 | 10.2564 | 0% | 0 | DNK | 0
1 | pe/EclipsePE | Post-integration editor test/debug/refine until usable | 11 | 0.72 | 15.2778 | 0% | 0 | DNK | 0
1 | pe/core, EclipsePE | Smart identifiers using Eclipse's parse tree, C++ only | 12 | 0.65 | 18.4615 | 0% | 0 | DNK | 0
2 | game/core | SDL video/audio/input, OpenGL linked and tested, project in github | 5 | 0.7 | 7.1429 | 0% | 0 | DNK | 0
2 | game/video | Resource loader: textures. PNG/procedural support. | 6 | 0.68 | 8.8235 | 0% | 0 | DNK | 0
2 | game/audio | Resource loader: sounds. WAV/procedural support. | 4 | 0.72 | 5.5556 | 0% | 0 | DNK | 0
2 | game/video | Resource loader: drawables. All procedural. Test by real drawing. | 9 | 0.67 | 13.4328 | 0% | 0 | DNK | 0
2 | game/video | Camera/Scene/Timer/Mainloop set. | 11 | 0.71 | 15.493 | 0% | 0 | DNK | 0
2 | game/model | World model and debug display (no delta, no Actors) | 10 | 0.75 | 13.3333 | 0% | 0 | DNK | 0
2 | game/model | World delta, Actors and Actions, delta tied to framerate | 9 | 0.73 | 12.3288 | 0% | 0 | DNK | 0
2 | game/model | Detach physics from framerate, multi-thread, 24fps, interpolate | 7 | 0.65 | 10.7692 | 0% | 0 | DNK | 0
2 | game/model | Integrate, test, debug, document. Playable physics milestone. | 10 | 0.72 | 13.8889 | 0% | 0 | DNK | 0
3 | game/video, game/model | Visual model. BG/FG/FFG (layers). Display this instead. | 8 | 0.76 | 10.5263 | 0% | 0 | DNK | 0
3 | game/video, game/model | Cache groups of statics as single Drawables | 6 | 0.69 | 8.6957 | 0% | 0 | DNK | 0
3 | game/video, game/model | Lighting and light actors, background tiles only | 10 | 0.65 | 15.3846 | 0% | 0 | DNK | 0
3 | game/video | Animation of actors, sprite sheet approach | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 0 | 0.7 | 0 | 0% | 0 | DNK | 0
|  |  | 138 |  | 197.2824 |  | 6 | 0.75 | 4.5
|  |  | units |  | est. hours |  | hours | real vel | real units